## Possible Risk
| Issue | Description | Possibilties | Potential Hazardousness | Mitigation Action
1 | Unable to meet deadline | Requirements or certain functionalities can not be deliveried within the required time | High | High | Set up internal deadline prior to the official deadline. Ask other group memebrs for help or search for alternatives.
2 | Misunderstand of requirements | Did not understand the client's requests or misunderstand them | High | High | Constantly check in with clients(e.g. via client meeting). Restate the client's requirements in your own words to ensure there are no misunderstandings.
3 | Fail to povide some functionalities on some platform | We observed that there're some packages only support certain platforms. We are trying to resolve all the dependency issues. | High | Medium | The minimum goal is to allow the project to work on at lesat one platform. Most of the issues are related to minor functionalities that we may find a way to replace except the Stripe issue. We will focus on dealing with Stripe first.
4 | Most of the work is from the previous semester | The IP agreement in the landing page has expired on 27/10/2023. | Medium | High | Separation of previous and current work, strengthening the distinction between the two and facilitating the development of milestones
5 | Technical obstacle | Certian functionalities can not be implemented due to some unsolveable problems | Medium | High | Reach for help from tutors and professors. Search for other alternatives.
6 | Lack of communication | Group memebrs and client are not famliar of each other's work and status | Medium | Medium | Regularly report work status to each other(via group meeting or communication platform). Explain to other memebrs your development plan.
7 | little decision making | the entire decision log consists solely of previous semester’s decisions | Medium | Medium | We need to develop clear decision-making and conflict resolution strategies, document each decision (and alternative), and improve the decision-making process as more data is collected.
8 | Conflicts in functionalities among different parts | Functionality overlapping between different sections is either redundantly developed or results in conflicts. | Medium | Medium | Team members share their development plans with each other to ensure that only one person is responsible for the same functionality, and to establish a unified development standard.
9 | Poor record of work traces | Team members, especially new members, may forget or are not used to recording work traces through Jira after work. | Medium | Medium | Team members should remind each other regularly, especially as the project progresses. It's a important habit to develop. Because the lack of work traces will lead to unclear contributions, lost context, Difficulty in Auditing, Challenge in Quality Assurance, content management confusion and many other problems.
10 | Low efficiency of meetings | Spending too much time on trivial issues and lacking communication efficiency. | Medium | Low | Plan ahead using meeting agenda. Everyone prepared before the meetings.
11 | Unexpected health problems | Sudden illness. | Low | Medium | Reassign the sick team member's workload to the remaining team members.

## Issue Record
No. | Issue | Description | Hazardousness | Mitigation Action | Date | Related Risk
1 | Conflicts between flutter version and firebase | We need firebase to support Stripe and used as our database. However the flutter version used in the previous semesters does not complie with the firebase. We need to change the version and migrate code to the latest version. | Cause lots of time to migrate. Bear the risks of migration failure. | Two memebrs work on migration and others work on function implementation using the latest version of flutter and adopt firebase as database. In this way we could ensure to achieve certain output at the end of semester. We set up check point to decide our further action. | 2023-03-14 | 8
2 | Flutter Stripe Package does not support web | Stripe does not provide flutter package. There is a flutter pacakage provided by dart pub. However this package does not support developing Stripe on Web | The client's requirement is to develop a cross-platform app. This would conflict with the initial goal. | We plan to develop a web page for payment form following Stripe's document. This may fail and cost extra time | 2023-04-15 | 9
3
4
5
6
7
8
9
10
11